## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-ID | Introduction to AI Market Trend & Sentiment Analysis Project | MUST HAVE | No Dependency | Entire Team | 3- Completed
Sprint 2 | Sprint 2 | US-ID | Define Workflow and Market Intelligence Goals | MUST HAVE | No Dependency | Entire Team | 3- Completed
Sprint 3 | Sprint 3 | US-ID | Design Architecture diagram | MUST HAVE | Lucidchart | Entire Team | 3- Completed
Sprint 4 | Sprint 4 | US-ID | Collect Multi-source Feedback Data (Amazon, Goodreads, YouTube, News) | MUST HAVE | Scrapers / APIs | Shahya | 3- Completed
Sprint 5 | Sprint 5 | US-ID | Clean & Merge Data into final_book_feedback.csv | MUST HAVE | Pandas | Shahya, Mayank | 3- Completed
Sprint 6 | Sprint 6 | US-ID | Perform Sentiment Analysis | MUST HAVE | NLP Model | Abhinav | 3- Completed
Sprint 7 | Sprint 7 | US-ID | Extract Topics and Aspects from Feedback | MUST HAVE | LLM Topic Model | Mayank | 3- Completed
Sprint 8 | Sprint 8 | US-ID | Implement RAG-based QA System | MUST HAVE | ChromaDB | Abhinav | 3- Completed
Sprint 9 | Sprint 9 | US-ID | Evaluate RAG Outputs with Real Queries | MUST HAVE | RAG System | Jothika | 3- Completed
Sprint 10 | Sprint 10 | US-ID | Develop UI for Question & Answer Display | MUST HAVE | Frontend Framework | Omkarendram | 3- Completed
Sprint 11 | Sprint 11 | US-ID | Build Trends & Complaints Dashboard | MUST HAVE | Processed Dataset | Entire Team | 3- Completed
Sprint 12 | Sprint 12 | US-ID | Prepare Final PPT & Documentation | MUST HAVE | All Modules | Abhinav | 3- Completed
Sprint 13 | Sprint 13 | US-ID | Final README & Integration Review | MUST HAVE | Full System | Shahya | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 56 | 18 | 17 | 12 | 5 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US_ID | 1 | Project Introduction & Objective Finalization | 29-12-25 | 2025-12-30 | Entire team | Others | Completed | 2 | bar: Day 1 to Day 2
US_ID | 2 | Define Market Intelligence Use Cases | 30-12-25 | 2025-12-31 | Shahya | Design | Completed | 1 | bar: Day 1
US_ID | 3 | System Architecture Design (RAG + Data Pipeline) | 31-12-25 | 2026-01-02 | Shahya | Design | Completed | 2 | bar: Day 1; Day 3
US_ID | 4 | Database & Vector Store Planning (ChromaDB Setup) | 2026-01-01 | 2026-01-04 | Mayank | Design | Completed | 4 | bar: Day 1 to Day 4
US_ID | 5 | Collect Ecommerce Book Reviews Dataset | 2026-01-01 | 2026-01-05 | Mayank | Build | Completed | 6 | Day 1: 1; Day 2: 2; Day 3: 2; Day 4: 1
US_ID | 6 | Collect YouTube Book Comments Dataset | 2026-01-05 | 2026-01-05 | Entire team | Build | Completed | 4 | bar: Day 1; Day 3 to Day 4; Day 6
US_ID | 7 | Merge & Clean Raw Datasets | 2026-01-08 | 2026-01-10 | Abhinav | Build | Completed | 3 | Day 1: 1; Day 2: 2
US_ID | 8 | Text Preprocessing & Noise Removal | 2026-01-10 | 2026-01-14 | Shahya | Build | Completed | 2 | bar: Day 1 to Day 2
US_ID | 9 | Sentiment Classification Implementation | 2026-01-14 | 2026-01-17 | Omkarendran | Build | Completed | 5 | Day 1: 1; Day 3: 1; Day 4: 1; Day 5: 2
US_ID | 10 | Embedding Generation & Vector Index Creation | 2026-01-17 | 2026-01-20 | Abhinav | Build | Completed | 6 | Day 1: 2; Day 2: 1; Day 3: 2; Day 5: 1
US_ID | 11 | Implement Retrieval Logic for RAG | 2026-01-20 | 2026-01-22 | Shahya | Test | Completed | 4 | bar: Day 1 to Day 4
US_ID | 12 | LLM Integration for Contextual Answer Generation | 2026-01-22 | 2026-01-24 | Jothika | Test | Completed | 2 | bar: Day 1; Day 3
US_ID | 13 | UI Design & Question Interface Development | 2026-01-24 | 2026-01-28 | Omkarendran | Build | Completed | 5 | Day 1: 1; Day 2: 3; Day 3: 1
US_ID | 14 | Backend–UI Integration & Testing | 2026-01-28 | 2026-02-03 | Omkarendran | Test | Completed | 3 | Day 1: 1; Day 2: 2
US_ID | 15 | RAG Evaluation & Query Performance Analysis | 2026-02-03 | 2026-02-18 | Jothika | Test | Completed | 3 | Day 1: 2; Day 3: 1
US_ID | 16 | Final PPT, Documentation & Final Presentation | 2026-02-18 | 2026-02-19 | Abhinav Mayank | Documentation | Completed | 4 | Day 1: 1; Day 2: 3

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 6 | Initial confusion in defining clear project scope and deliverables | Conducted team discussion and finalized objectives and workflow
Sprint 2 | Day 8 | Difficulty in collecting structured datasets from multiple sources | Standardized data format and created common CSV schema
Sprint 3 | Day 10 | Presence of noisy and duplicate data in raw datasets | Applied preprocessing, removed duplicates, cleaned text
Sprint 4 | Day 18 | Sentiment model misclassifying neutral reviews | Fine-tuned preprocessing and adjusted classification thresholds
Sprint 5 | Day 23 | RAG retrieval returning generalized answers | Improved chunking strategy and refined embedding process
Sprint 6 | Day 29 | Backend and UI integration delay | Conducted debugging session and resolved API connection issues
Sprint 7 | Day 38 | Some queries failing due to insufficient context | Added fallback response and improved retrieval filtering
Sprint 8 | Day 45 | Performance slowdown with larger dataset | Optimized vector indexing and reduced redundant embeddings
Sprint 9 | Day 52 | Need for clearer trend visualization in UI | Added structured summary section for top complaints and trends

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-12-29 | 2026-01-05 | Entire Team | Define clear project roadmap | Working without documentation | Collaborative planning | Created structured workflow document
2 | Sprint 2 | 2026-01-06 | 2026-01-15 | Mayank | Collect multi-source datasets | Relying on single dataset | Data validation process | Merged datasets into unified CSV
3 | Sprint 3 | 2026-01-16 | 2026-01-26 | shahya | Improve preprocessing pipeline | Ignoring neutral sentiments | Sentiment evaluation | Added text normalization & cleaning
4 | Sprint 4 | 2026-01-27 | 2026-02-03 | Jothika | Optimize RAG retrieval | Large text chunks | Context-based answering | Improved embedding & chunking
5 | Sprint 5 | 2026-02-04 | 2026-02-05 | Omkarendran | Enhance UI interaction | Static text-only display | User-friendly interface | Integrated backend with UI
6 | Sprint 6 | 2026-02-06 | 2026-02-10 | Abhinav | Improve documentation quality | Last-minute documentation | Proper reporting | Updated README & final PPT
7 | Sprint 7 | 2026-02-11 | 2026-02-15 | Entire Team | Add evaluation metrics | Relying only on qualitative analysis | Query testing | Documented RAG evaluation process